| No. | Item |  |  | Yes | No | Remark |
| --- | --- | --- | --- | --- | --- | --- |
|  | Project Properties |  |  |  |  |  |
|  | Submission of Work Program (Latest Version of MS Project used) |  |  |  |  |  |
|  | Project Name |  |  |  |  |  |
|  | Project Information is according to LOA |  |  |  |  |  |
|  | Scheduling Pattern (only Forward Path applied) |  |  |  |  |  |
|  | Work Breakdown Structure |  |  |  |  |  |
|  | WBS |  |  |  |  |  |
|  | - All scope has been listed in logical manner according to construction sequences |  |  |  |  |  |
|  | - All milestone has been included in the program |  |  |  |  |  |
|  | WBS Level Minimum of 4 task level |  |  |  |  |  |
|  | WBS (other consideration) |  |  |  |  |  |
|  | - External milestone identified |  |  |  |  |  |
|  | - Internal Milestone identified |  |  |  |  |  |
|  | - Recurring Task identified |  |  |  |  |  |
|  | - Split Task is not allowed |  |  |  |  |  |
|  | Calendar |  |  |  |  |  |
|  | Working days has been specified according to condition of contract |  |  |  |  |  |
|  | Public Holiday has been specified for the entire contract period |  |  |  |  |  |
|  | Ensure working hours is according to condition of contract |  |  |  |  |  |
|  | Cost Budgeting |  |  |  |  |  |
|  | Total cost estimated is equal to project contract sum |  |  |  |  |  |
|  | Cost is entered in the fixed cost column only |  |  |  |  |  |
|  | Cost to be filled to all task except milestone and external dependencies |  |  |  |  |  |
|  | Other Parameter |  |  |  |  |  |
|  | There is an absolute and clear critical path |  |  |  |  |  |
|  | All task have been auto-scheduled |  |  |  |  |  |
|  | There are no negative total slack for all task |  |  |  |  |  |
|  | Financial S-curve is logic, workable and manageable |  |  |  |  |  |
|  | Physical S-curve is logic, workable and manageable |  |  |  |  |  |
|  | Appropriate timescale being used |  |  |  |  |  |
|  | The submitted work programme is presentable |  |  |  |  |  |
|  | - Project Title is inserted in the header section |  |  |  |  |  |
|  | - Respective Client and Contractor’s name are inserted in the footer section |  |  |  |  |  |
| Prepared by (Planning Engineer) |  | Reviewed by (Project Manager) | Approved by (Director) |  |  |  |
| Signature |  | Signature | Signature |  |  |  |
| Name: |  | Name: | Name: |  |  |  |
| Date : |  | Date : | Date : |  |  |  |